OVERVIEW OF THE PROCUREMENT PROCESS

| OJEU issued |  | Descriptive document (information pack) and PQQ issued on receipt of expressions of interest |  | Final Date for return of PQQs |  | PQQ Evaluation and shortlist of bidders [Preference is to shortlist not more than 4] |
| --- | --- | --- | --- | --- | --- | --- |
| Friday 18th December 2009 |  |  |  | Friday 29th January 2010 | 2weeks | Thursday 11th February 2010 |
| Open competitive dialogue and issue invitation to submit detailed solutions to shortlisted bidders |  | Bid period and competitive dialogue leading to submission of detailed solutions |  | Evaluation of detailed solutions Deselection of 1/2 bidder(s) |  | Further dialogue and refinement of solutions with remaining bidders |
| Friday 12th February 2010 | 12 weeks | Friday 7th May 2010 | 5 weeks | Friday 11th June 2010 | 8 weeks | Friday 6th August 2010 |
| Close competitive dialogue and call for final tenders |  | Final tenders returned |  | Final evaluation and preferred partner selected |  | Sign Contracts |
| Friday 6th August 2010 | 2 weeks | Friday 20nd August 2010 | 6 weeks | Friday 30th September 2010 |  | Friday 17th December 2010 |